## Sheet1
Schedule Management
Project Name: Hunt Game App Development | Date: 08/23/2020
Estimated Hours per person
Work Breakdown Structure Categories | Start Date | End Date | Responsible | Krishna | Swaroop | Yashwanth | Prasad | Sudheera | Sai Krishna | Total Hrs
1. Initiating | 2020-08-24 | 2020-08-31 | Team | 2 | 2 | 2 | 2 | 2 | 2 | 12
2. Planning | 2020-08-31 | 2020-09-09 | Team | 2 | 2 | 2 | 2 | 1 | 3 | 12
3. Designing | 2020-09-09 | 11/31/2020 | Team
3.1 UI Design | 2020-09-09 | 2020-09-15 | Prasad | 2 | 1 | 3 | 3 | 1 | 2 | 12
3.2 Synthesis of Design | 2020-09-16 | 2020-10-15 | Team | 2 | 2 | 2 | 2 | 1 | 3 | 12
3.3 Implementation Iteration | 2020-10-16 | 2020-11-04 | Swaroop | 3 | 3 | 2 | 1 | 2 | 1 | 12
3.4 Early release and Contract finalization | 2020-11-05 | 11/31/2020 | Krishna | 2 | 3 | 3 | 1 | 1 | 1 | 12
4. Implementation | 2021-01-20 | 2021-03-28 | Team
4.1 Application Development | 2021-01-20 | 2021-02-05 | Team | 4 | 4 | 4 | 4 | 4 | 4 | 24
4.2 PWA Implementation | 2021-02-06 | 2021-02-28 | Yashwanth | 4 | 4 | 4 | 4 | 4 | 4 | 24
5. Monitoring and Controlling | 2021-04-03 | 2021-04-17 | Sai Krishna | 2 | 2 | 2 | 2 | 2 | 2 | 12
6. Closing | 2021-04-18 | 2021-05-01 | Sudheera | 2 | 2 | 2 | 2 | 2 | 2 | 12
|  |  | Total | 19 | 19 | 20 | 17 | 15 | 17 | 108